## Schedule
Phase | Task / Milestone | Description | Start date | Planned finish date | Actual finish date | Dependency | Comment
Phase I - R&D | 2 | Finalize R&D TOF design | 2019-02-01 | 2019-06-01 |  |  | Need Design Eng
| 4 | Simulate reducing signal | 2019-02-01 | 2019-06-01 |  |  | Ongoing
| 6 | Iterate Simulation and Eng. Design of R&D TOFs | March/April 2019 | 2019-07-01 |  |  | Ongoing
| 8 | Order 2 initial R&D TOFs | 2019-05-01 | 2019-08-01
| 10 | Order 6 R&D TOFs | 2019-09-01 | 2019-12-01
| 12 | Initial Digitizer arrival | 2019-01-01 | 2019-05-01
| 14 | Other three digitizers | 2019-05-01 | Sept. 2019
| 16 | Iterate Chamber Eng. Design | 2019-06-01 | 2019-08-01
| 18 | Order initial R&D MCP (2) | 2019-05-01 | 2019-08-01
| 20 | Order full set of R&D MCPs (6) | 2019-07-01 | Nov. 2019
| M1 | Prototype Chamber Final Design |  | 2019-08-01 |  | 16 | PEC for XIP
Phase II? | 22 | Order Prototype mu metal chamber | 2019-09-01 | 2020-01-01 |  | M1 | Lead time = 3-6 months
| 24 | Assemble Prototype | 2019-12-01 | Feb. 2020 |  | M1, 22 | need 4-6 weeks
| M2 | (Adjust) Final Design TMO version Chamber Design and make FDR | 2019-12-01 | Feb. 2020 |  |  | XIP FDR
Phase II - XIP | 28 | Order Parts | 2020-01-01
| 30 | Assemble | 2020-07-01
| 32 | Test | 2020-08-01
| 34 | Offline commissioning | 2020-10-01
| M3 | RFI
| 36 | Install MRCOFFE in TMO | 2020-12-01
| M4 | TTO
| M5 | Project closeout